## Roles
Roles | Name
Web Designer | Ta Duc, Hung Vu
Scrum Master | Hung Vu
Programmers | Mac Hung, Toan, Trung Duc
DB designer | Mac Hung
Tester | Igbo Kingsley Chinedu

## Meetings
Day(2020) | Meeting | Members | Day 2 | Day 4
25/3-28/3 | What did you do on yesterday? | Trung Đức | I learned about how to install the firebase SDK on the web app and the structure of the react language | I finished creating config for app
Sprint 1 |  | Tạ Đức | i learned how to design dashboard UI for student and draw wireframe | i finished designing dashboard UI for student and drawing wireframe
|  | Vũ Hùng | I learned about how to draw wire frame for dash board | I finished draw Use case diagram
|  | Mạc Hùng | I learned about how to install the firebase SDK on the web app and the structure of the react language | I finished creating config for app
|  | Toàn | Familiarize yourself with firebase, syntax, data, queries
Igbo
| What will you do on tomorrow? | Trung Đức | I will research and continute breaking components
|  | Tạ Đức | design dashboard UI for student and draw wireframe
|  | Vũ Hùng | I will draw dash board to tutor and student | I will start draw wire frame for admin
|  | Mạc Hùng | I will research and continute breaking components
|  | Toàn | Based on the requirements to create the database
Ibgo
| Do you have any problem? | Trung Đức | I have difficulty breaking down into components
|  | Tạ Đức | no have problem
|  | Vũ Hùng | I have some problems while design Use case diagram | May be not
|  | Mạc Hùng | I have difficulty breaking down into components
|  | Toàn | I had difficulty getting used to Firebase and NoSql queries
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
29/3-1/4 | What did you do on yesterday? | Trung Đức | I learned about authentication api on firebase | I finished creating google authentication but can select data from db
Sprint 2 |  | Tạ Đức | draw wireframe and design UI for accessed data
|  | Vũ Hùng | I drawed the wire frame | I did not do any thing yesterday
|  | Mạc Hùng | I learned about authentication api on firebase
|  | Toàn | Complete 2 databases of students and tutors
Igbo
| What Will you do on tomorrow? | Trung Đức | finish login function by decentralization
Tạ Đức
|  | Vũ Hùng | I will draw wire frame for database | I will do the sprint 1 and finish the burn down chart of sprint 1
|  | Mạc Hùng | finish login function by decentralization
|  | Toàn | Complete the database of assigning students and tutors
Ibgo
| Do you have any problem? | Trung Đức | I get stuck when i want to make decentralization
Tạ Đức
|  | Vũ Hùng | i have no idea to do it | I don't know how to do it
|  | Mạc Hùng | I get stuck when i want to make decentralization
|  | Toàn | No anything
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
2/4-5/4 | What did you do on yesterday? | Trung Đức
Sprint 3 |  | Tạ Đức | learn how to design message UI for student and draw wireframe for it | i finished designing message UI for student and drawing wireframe
|  | Vũ Hùng | Continuned do the report group | I finished the burn down chart of sprint 3
Mạc Hùng
Toàn
Igbo
| What will you do on tomorrow? | Trung Đức
|  | Tạ Đức | design message UI for student and draw wireframe
|  | Vũ Hùng | Finish the burn down chart for sprint 3 | I will assign the user interface in out report
Mạc Hùng
Toàn
Ibgo
| Do you have any problem? | Trung Đức
|  | Tạ Đức | nothing
|  | Vũ Hùng | There are many information that i have to add in report | Maybe I don't have problem
Mạc Hùng
Toàn
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
6/4-9/4 | What did you do on yesterday? | Trung Đức | I got understand about noSQL database | I finished meeting function
Sprint 4 |  | Tạ Đức | learn how to design meeting UI for student and draw wireframe for it | i finished designing meeting UI for student and drawing wireframe
|  | Vũ Hùng | I finished assign the user interface image in report | I finished the burn down chart of sprint 4
Mạc Hùng
Toàn
Igbo
| What will you do on tomorrow? | Trung Đức | I will find out firestore query
|  | Tạ Đức | design meeting UI for student and draw wireframe
|  | Vũ Hùng | I will finish the burn down chart of sprint 4 | I will do the scrum documents
Mạc Hùng
Toàn
Ibgo
| Do you have any problem? | Trung Đức | I get stuck when i select query in firestore
|  | Tạ Đức | nothing
|  | Vũ Hùng |  | No problems
Mạc Hùng
Toàn
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
10/4-13/4 | What did you do on yesterday? | Trung Đức | i learned about firestore to save fire in storage | I finished posting funtion without no file
Sprint 5 |  | Tạ Đức | I researched how to design ERD | i finished designing ERD
|  | Vũ Hùng | I finished the scrum documents
Mạc Hùng
Toàn
Igbo
| What will you do on tomorrow? | Trung Đức | Continute learning firebase storage
|  | Tạ Đức | design ERD
|  | Vũ Hùng | I will draw the burn down chart of sprint 5
Mạc Hùng
Toàn
Ibgo
| Do you have any problem? | Trung Đức | I can't get file from input
Tạ Đức
|  | Vũ Hùng | I don't know how to evaluate
Mạc Hùng
Toàn
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
14/4-17/4 | What did you do on yesterday? | Trung Đức
Sprint 6 |  | Tạ Đức | i researched tutor's functions | i finished my work in this sprint
Vũ Hùng
Mạc Hùng
|  | Toàn | Complete client-side programming for showing unsupported students and tutors lists
Igbo
| What will you do on tomorrow? | Trung Đức
|  | Tạ Đức | i will draw tutor's functions and describe for it
Vũ Hùng
Mạc Hùng
|  | Toàn | Completing client-side programming for showing Contacts lists of students who do not yet have support with tutors
Ibgo
| Do you have any problem? | Trung Đức
Tạ Đức
Vũ Hùng
Mạc Hùng
|  | Toàn | Having trouble with the lifecycle of ReactJs
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
18/4-21/4 | What did you do on yesterday? | Trung Đức
Sprint 7 |  | Tạ Đức | i researched student's functions | i finished drawing student's funtions and description for it
|  | Vũ Hùng | I did not do any thing | I finished draw the burn down chart of sprint 6
Mạc Hùng
|  | Toàn | Complete retrieving data of students and tutor from database
Igbo
| What will you do on tomorrow? | Trung Đức
|  | Tạ Đức | i will draw student's functions and describe for it
|  | Vũ Hùng |  | I will finished the burn down chart of sprint 7
|  | Mạc Hùng | I will finish the burn down chart of sprint 6
|  | Toàn | Complete retrieving the contact data between students and tutors and adding data to the database
Ibgo
| Do you have any problem? | Trung Đức
Tạ Đức
|  | Vũ Hùng |  | I have some error when i finish the sprint
Mạc Hùng
|  | Toàn | I have difficulty with complex firebase queries
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
22/4-25/4 | What did you do on yesterday? | Trung Đức | i learned about route and useContext in react | I finished my code
|  | Tạ Đức | i researched our code | i described how our code is clean
Sprint 8 |  | Vũ Hùng | I finished the burndown chart of sprint 7 | I finished the burn down chart of sprint 8
Mạc Hùng
Toàn
Igbo
| What will you do on tomorrow? | Trung Đức | I try my best to find solution
|  | Tạ Đức | i describe how our code is clean
|  | Vũ Hùng | I will finished the form and check the sprint 8 | I will finish the burn down chart of sprint 9
Mạc Hùng
Toàn
Ibgo
| Do you have any problem? | Trung Đức | I get stuck to get param from link
Tạ Đức
|  | Vũ Hùng | Some people did not done their sprint | Maybe not
Mạc Hùng
Toàn
Igbo
Day(2020) | Meeting | Members | Day 2 | Day 4
26/4-29/4 | What did you do on yesterday? | Trung Đức
Tạ Đức
|  | Vũ Hùng | Finished the Burn down chart for sprint 9 | Finished the Burn down chart
Mạc Hùng
Toàn
Igbo
| What will you do on tomorrow? | Trung Đức
Tạ Đức
|  | Vũ Hùng | Do the Evaluation of report | I will check the form and content and fix bugs
Mạc Hùng
Toàn
Ibgo
| Do you have any problem? | Trung Đức
Tạ Đức
|  | Vũ Hùng | I think I don't have any problem | No problem
Mạc Hùng
Toàn
Igbo

## Product backlog
ID | AS a/an | I want to … | So that… | Priority | Sprint | Status
1 | As a student | I want to have a personal tutor to guide me | So that I can contact to tutor | Must have | 4 | Done
2 | As a student | I want to messaging to personal tutor | So that I can exchange with tutor | Must have | 5 | not yet
3 | As a student | I want to my data is accessed from the university MIS system. | So that I can login/logout | Must have | 3 | Not yet
4 | As a student | I want to each student will have their own personal dashboard summarising their interaction with their personal tutor. |  | Must have | 1 | Done
5 | As a student | I want to verify meetings | So that I can be sure to join meeting | Should have | 6 | Done
6 | As a student | I want to commenting on tutor post | So that I can interact with tutor | Should have | 7 | Done
7 | As a student | I want to get notification of events recorded meeting |  | Could have | 9
8 | As an authorized member | I want to dashboards to manage student and tutor | So that I can manage them | Must have | 2 | Done
9 | As an authorized member | I want to llocate or reallocate personal tutors to students. | So that I can manage contact | Must have | 4
10 | As an authorized member | I want to The student and the personal tutors will get notification emails when this happens |  | Should have | 8 | Not Do
11 | As an authorized member | I want to assign to many students at a time to tutor | So that I can save time | Should have | 8
12 | As an authorized member | I want to filtering students without a personal tutor |  | Could have | 11
13 | As an authorized member | I want to filtering students with no interaction |  | Could have | 11
14 | As an authorized member | I want to be Notify when a student is absent |  | Could have | 11
15 | As a tutor | I want to arrange meetings |  | Must have | 6 | Done
16 | As a tutor | I want to messaging to students | So that I can exchange with student | Must have | 5
17 | As a tutor | I want to each personal tutor will have a dashboard of their personal tutees that can be sorted and filtered appropriately |  | Must have | 1 | Done
18 | As a tutor | I want to my data is accessed from the university MIS system. | So that I can login/logout | Must have | 3 | Done
19 | As a tutor | I want to make of post for uploading document and commenting on them and for blogging | So that I can notify all students | Should have | 7 | Not yet
20 | As a User | I want to the interface must be suitable for all devices (eg mobile phones, tablets, desktops) |  | Should have | 10 | Not yet
21 | As a tutor | I want to get notification when student verify meeting |  | Could have | 9

## Sprint 1
User Story | Tasks | Member | Status | Estimated Hours of Completion | Day 1 | Day 2 | Day 3 | Day 4 | Review
| Draw wireframe | Chinedu | Done | 25/03 - 2 hours | 2 | 0 | 0 | 0 | 0
| Front end coding for dashboard | Chinedu | Done | 20 hours | 10 | 10 | 5 | 0 | 0
As a tutor, I want to each personal tutor will have a dashboard of their personal tutees that can be sorted and filtered appropriately | Create database | N.T.D | Done | 20 hours | 20 | 15 | 10 | 0 | 0
| Back-end coding | N.T.D | Done | 30 hours | 30 | 20 | 10 | 0 | 0
| Testing | Chinedu | Done | 2 hours | 2 | 2 | 2 | 0 | 0
As a student, I want to each student will have their own personal dashboard summarising their interaction with their personal tutor. | Draw wireframe | T.V.D | Done | 2 hours | 2 | 0 | 0 | 0 | 0
| Front end coding | T.V.D | Done | 9 hours | 9 | 4 | 2 | 0 | 0
| Create database | M.H | Done | 5 hours | 5 | 0 | 0 | 0 | 0
| Back-end coding | M.H | Done | 14 hours | 6 | 5 | 1 | 0 | 0
| Testing | T.V.D | Done | 1 hours | 1 | 1 | 1 | 0 | 0
As an authorized member , I want to dashboards to manage student and tutor | Draw wireframe | Hung Vu | Done | 2 hours | 1 | 1 | 0 | 0 | 0
| Front end coding | Hung Vu | Done | 10 | 10 | 6 | 3 | 0 | 0
| Create database | Toan | Done | 2 | 5 | 5
| Back-end coding | Toan | Done | 20 | 15 | 12 | 7 | 0 | 0
| Testing | Hung Vu |  | 2 | 2 | 0 | 0 | 0 | 0

## Sprint 2
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As a tutor, I want to my data is accessed from the university MIS system. | Draw wireframe | Chinedu | Done | 2 hours | 1 | 0 | 0 | 0 | 0
| Front end coding | Chinedu | Done | 5 hours | 2 | 0 | 0 | 0 | 0
| API Making | N.T.D | Done | 5 hours(31/3/2020) | 5 | 0 | 0 | 0 | 0
| Back-end coding | N.T.D | OnGoing | 10 hours | 5 | 5 | 5 | 3 | 3
| Testing | Chinedu | Not yet | 1 | 1 | 1 | 1 | 1 | 1
| Draw wireframe | T.V.D | Done | 3 hours | 3 | 0 | 0 | 0 | 0
| Front end coding | T.V.D | Done | 3 hours | 3 | 0 | 0 | 0 | 0
| API Making | M.H | Done | 4 hours | 3 | 1 | 0 | 0 | 0
As a student, I want to my data is accessed from the university MIS system. | Back-end coding | M.H | Done | 5 hours | 2 | 2 | 1 | 0 | 0
Testing
| Draw Wire frame | Hung Vu | Done | 2 hours | 2 | 0 | 0 | 0 | 0
As an authorized member , I want to my data is accessed from the university MIS system. | Front-end Coding | Toan | Done | 5 | 5 | 3 | 1 | 0 | 0
| Back-end Coding | Toan | Done | 10 | 10 | 8 | 5 | 0 | 0
| Create Databese | Toan | Done | 3 | 3 | 0 | 0 | 0 | 0
| Test | Chindo | Done | 1 | 1 | 1 | 1 | 0 | 0

## Sprint 3
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As a tutor, I want to messaging to students | Draw wifeframe | chinedu | Done | 2 | 1 | 1 | 0 | 0 | 0
(Base on student code of M.X.H) | Font end coding | chinedu | Done | 5 | 3 | 5 | 3 | 2 | 0
| Create collection database | N.T.D | Done | 10 | 7 | 5 | 3 | 0 | 0
| Back end coding | N.T.D | Not Done | 12/04/2020 - 20 hours | 20 | 20 | 10 | 10 | 0
| storage file (firebase storage) | N.T.D | Done | 10 | 10 | 12 | 5 | 1 | 0
As a student, I want to messaging to personal tutor | Draw wifeframe | TVD | Done | 2 hours | 2 | 0 | 0 | 0 | 0
| Font end coding | T.V.D | Done | 8 hours | 3 | 5 | 0 | 0 | 0
| Create collection database | M.H | Done | 12/04/2020 - 20 hours | 3 | 4 | 4 | 0 | 0
| Back end coding | M.H | Done | 12/04/2020 - 5 hours | 1 | 3 | 1 | 0 | 0
| storage file (firebase storage) | M.H | Done | 12/04/2020 - 10 hours | 3 | 5 | 0 | 0 | 0

## Sprint 4
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As a tutor ,I want to arrange meetings | Draw wifeframe | chinedu | Done | 3 hours | 3 | 0 | 0 | 0 | 0
(Base on code of N.T.D) | Font end coding | chinedu | Done | 9 hours | 7 | 3 | 0 | 0 | 0
| Create collection database | N.T.D | Done | 10 hours | 1 | 0.5 | 0 | 0 | 0
| Back end coding | N.T.D | Done | 10 hours | 5 | 8 | 5 | 0 | 0
| Test log | chinedu | Done | 2 | 2 | 2 | 2 | 0 | 0
| Draw wifeframe | TVD | Done | 3 hours | 3 | 0 | 0 | 0 | 0
| Font end coding | TVD | Done | 15 hours (19/4/2020) | 3 | 4 | 3 | 0 | 0
As a student, I want to verify meetings | Create collection database | M.H | Done | 10 hours (19/4/2020) | 10 | 6 | 3 | 0 | 0
| Back end coding | M.H | Done | 15 hours (19/4/2020) | 5 | 2 | 3 | 0 | 0

## Sprint 5
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As a tutor, I want to make of post for uploading document and commenting on them and for blogging | Draw wifeframe | Chinedu | Done | 1 | 1 | 0 | 0 | 0 | 0
| Font end coding | Chinedu | Done | 10 | 10 | 0 | 0 | 0 | 0
| Create collection database | N.T.D | Done | (23/04/2020) 10 | 10 | 5 | 5 | 3 | 0
| Back end coding for posting | N.T.D | Not Done | 20 hours | 30 | 20 | 10 | 0 | 0
| Setting save file storage | N.T.D | Done | 20 hours | 20 | 25 | 10 | 0 | 0
| Coding comment function | N.T.D | Not Done | 20 hours | 20 | 14 | 8 | 0 | 0
| Test | Chinedu | Done | 2 hours | 2 | 2 | 2 | 2 | 0

## sprint 6
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
| Front end Coding | Toan | Done | 5 hours | 5 | 2 | 0 | 0 | 0
As an authorized member, I want to llocate or reallocate personal tutors to students. | Back-end coding | Toan | Done | 5 hours | 5 | 2 | 0 | 0 | 0
| Testing | Chinedu | Done | 1 hours | 1 | 1 | 0 | 0 | 0
| Fornt end coding | Toan | Done | 2 hours | 2 | 0 | 0 | 0 | 0
As an authorized member , I want to assign to many students at a time to tutor | Back end coding | Toan | Done | 5 hours | 5 | 2 | 0 | 0 | 0
| Testing | chinedu | Done | 1 hours | 1 | 1 | 0 | 0 | 0
| Front end code | Toan | Done | 5 hours | 5 | 3 | 1 | 0 | 0
As an authorized member ,I want to filtering students without a personal tutor | back end coding | Toan | Done | 5 hours | 8 | 4 | 2 | 0 | 0
| Testing | chinedu | Done | 1 hours | 1 | 1 | 1 | 0 | 0

## Sprint 7
User Story | Tasks | member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As an authorized member ,I want to be Notify when a student is absent | Front end code | Toan |  | 5 hours | 5 | 3 | 0 | 0 | 0
| back end code | Toan |  | 5 hours | 5 | 2 | 0 | 0 | 0
| Testing | Chinedu |  | 1 hours | 1 | 1 | 0 | 0 | 0
| Front end code | Toan | Done | 5 hours | 5 | 2 | 0 | 0 | 0
As an authorized member ,I want to filtering students with no interaction | back end code | Toan | Done | 15 hours | 15 | 10 | 4 | 0 | 0
| Testing | Chinedu | Done | 1 hours | 1 | 1 | 1 | 0 | 0

## Sprint 8
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
| Front end code | M.X.H | Done | 1/05/2020 2 hours | 2 | 0 | 0 | 0 | 0
As a student,I want to commenting on tutor post | Back end code | Duc | Done | 5 hours | 5 | 1 | 0 | 0 | 0
| Testing | Chinedu | Not yet | 1 hours | 1 | 1 | 0 | 0 | 0

## Sprint 9
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
As a student, I want to get notification of events recorded meeting | Front end code | M.X.H | Done | 2/05/2020 2 hours | 2 | 0 | 0 | 0 | 0
| Back end code | N.T.D | Done | 5 hours | 5 | 0 | 0 | 0 | 0
| Testing | Chinedu | Done | 1 hours | 1 | 0 | 0 | 0 | 0

## sprint 10
User Story | Tasks | Member | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Review
I want to the interface must be suitable for all devices (eg mobile phones, tablets, desktops) | Front end code | T.V.D | Done | 5 hours | 5 | 0 | 0 | 0 | 0
| Testing | Chinedu |  | 1 | 1 | 0 | 0 | 0 | 0